## Sheet1
Defect ID | Priority | ACN Severity | Environment | Type | Summary | Status | Creation Date | Expected Resolution Date | DEV OWNER | Root Cause | UAT | PROD | CT OWNER
Defect_-1055 | 1 | MEDIUM | BAU | TASK | BAU-488103-E-Fesih SCO Ek Gereksinim | FIXED | 2021-07-01 | 2021-07-05 | GÜLFEM
Defect_-1056 | 2 | MEDIUM | BAU | DEFECT | BAU- Akıllı Şehirler Endpoint Güncelleme | FIXED | 2021-07-01 | 2021-07-05 | SEDANUR
Defect_-1057 | 3 | HIGH | ALL | TASK | BAU- WSDL Güncellemesi Retrieve Segmenta | RESOLVE | 2021-07-02 |  | SONER
Defect_-1048 | 4 | MEDIUM | BAU | DEFECT | BAU- 424874- SMS ve Email iletilmemesi | ON CT | 2021-06-28 | 2021-07-02 | SEDANUR
Defect_-1050 | 5 | LOW | BAU | DEFECT | BAU- 488103- SMS Servisinden hata alımı | ON CT | 2021-06-30 | 2021-07-08 | GÜLFEM
Defect_-1047 | 6 | MEDIUM | PROD | IR | PROD-Merge Mesajı Yansımayan Müşteri ALM:241517 | ON CT | 2021-06-28 |  | OZAN
Defect_-1053 | 7 | MEDIUM | PROD | TASK | PROD - SFA Aktarım | RESOLVE | 2021-06-30 |  | GÜLFEM
Defect_-1033 | 8 | MEDIUM | DEV | TASK | DEV- SMTP Ortamının DEVde Aktif Edilmesi | RESOLVE | 2021-06-23 |  | OZAN
Defect_-1032 | 9 | MEDIUM | PROD | DEFECT | PROD- Müşteri Seri Noları Silinmesi | ON CT | 2021-06-23 |  | GÜLFEM
Defect_-996-239491 | 10 | MEDIUM | PROD | IR | PROD- Kurumsal musterinin OM bilgisinin TMS olarak kalmasi hk ALM:239491 | ON CT | 2021-06-09 |  | GÜLFEM
Defect_-1034 |  | MEDIUM | DEV | TASK | DEV- SMS/Email Loglama | FIXED | 2021-06-23 |  | İBRAHİM
Defect_-1054 |  | MEDIUM | BAU | TASK | 488103- BAU - E Fesih - URL Geliştirmesi | FIXED | 2021-07-01 | 2021-07-05
Defect_-1004 |  | MEDIUM | ALL | DEFECT | Güvenlik Defecti-186777 | ON CT | 2021-06-15 |  | SEDANUR
Defect_-931 |  | MEDIUM | ALL | DEFECT | Güvenlik Defecti - 186780 | ON CT | 2021-04-13 |  | SONER |  |  |  | ÜMMÜHAN
Defect_-987-239292 |  | MEDIUM | PROD | IR | PROD - Ana Neden Kodu Çıkmaması Hakkında ALM:239292 | ON CT | 2021-06-07 | [5 empty] | ÜMMÜHAN
Defect_-977 |  | MEDIUM | PROD | DEFECT | PROD- Hatalı Sanitizasyon Yapılması | ON CT | 2021-05-27 |  | SONER
Defect_-952 |  | MEDIUM | PROD | DEFECT | PROD- BTK 1-4 Geçişi Not Girilmeden | ON CT | 2021-05-03
Defect_-832-228169 |  | MEDIUM | UAT | DEFECT | UAT-OHM DE ACILAN THK PSTN ARIZASININ IYS YE DUSMEMEMSI HK. ALM:228169 | ON CT | 2021-02-16 | 2021-02-20